CERTAIN-COAST — Work Plan

Certified early warning for seawater intrusion, liquefaction and extreme sea levels at the wellfields, port and energy landfall of a subsiding Adriatic coast

1. Structure and logic

The project runs for 36 months in seven work packages. WP1 to WP6 deliver objectives O1 to O6 one to one, so the deliverable codes of the objectives are kept; WP7 manages the whole. The logic runs in three phases:

• Measure and design (Months 1–12). WP1 measures the coastal motion and WP4 designs and installs the monitoring network; both start at once because the network design needs only existing and remote-sensing data.

• Model and certify (Months 4–30). WP2 builds and calibrates the coupled model and its fast surrogate on the data of WP1 and WP4; WP3 turns the forecasts into certified alarms and tests them on the historical record and on storylines beyond it.

• Operate and hand over (Months 22–36). After the go/no-go milestone MS4, WP5 runs the system live for twelve months with the operators; WP6 trains the people who will run it after the project and releases the software and procedures.

Data flow between the work packages: WP1 → WP2 (relative sea level R(t), compaction parameters); WP4 → WP2, WP3 (heads, chloride, seismic velocity in real time); WP2 → WP3 (forecasts and their error bounds); WP3 → WP5 (alarms with margins); WP5 → WP3, WP6 (verified outcomes, operating experience). WP4 also receives from WP3 the value of each sensor for the warnings, so the network can be refined in Year 2.

2. Work packages

WP1. Coastal motion and relative sea level   (Months 1–36; objective O1)

Objective: Measure the vertical motion of the land at the wellfields, the port and the landfall, separate what pumping can reverse from what it cannot, and deliver the relative sea level R(t) that drives every hazard model.

| Task | Description | Months |
| --- | --- | --- |
| T1.1 | Sentinel-1 InSAR time series (2014 onwards) over the three asset areas | M1–M9 |
| T1.2 | GNSS station(s) and corner reflectors at the assets; tie to the tide gauge | M3–M36 |
| T1.3 | Elastic and inelastic compaction separated; pumping limit without inelastic compaction; 2019 coseismic and postseismic motion | M6–M12 |
| T1.4 | R(t) series with uncertainty at each asset, updated through the demonstration | M10–M36 |

Deliverables: D1.1 Coastal motion atlas and R(t) series (Month 12)

WP2. One coupled model of the coast and its certified fast copy   (Months 4–24; objective O2)

Objective: Build and calibrate one physical model that gives, from the same forcing, the chloride at the wells, the liquefaction factor of safety at the port and the landfall, and the extreme water level at all three; and a fast surrogate with an error bound on every forecast.

| Task | Description | Months |
| --- | --- | --- |
| T2.1 | Conceptual model and data assembly: geology, wells, port and landfall geotechnical data | M4–M9 |
| T2.2 | Coupled model: variable-density flow, salt memory, compaction, FS(x,t) = CRR/CSR(z_w), coastal water level on R(t) | M7–M15 |
| T2.3 | Calibration on heads, conductivity, chloride, InSAR and seismic velocity | M12–M18 |
| T2.4 | Neural or kernel operator surrogate with a-posteriori error bound | M15–M22 |

Deliverables: D2.1 Calibrated coupled model (Month 18); D2.2 Certified surrogate (Month 22)

WP3. Certified multi-hazard alarm   (Months 13–34; objective O3)

Objective: Turn the forecasts into alarms whose miss rates are bounded: a margin made of the surrogate error bound, an online conformal risk-control term and an extreme-aware term; a joint guarantee over the three hazards.

| Task | Description | Months |
| --- | --- | --- |
| T3.1 | Hazard indicators and thresholds agreed with the operators (chloride limit, FS < 1, design water level) | M13–M15 |
| T3.2 | Margin construction and proofs: error bound + online conformal risk control + extreme-aware term | M15–M24 |
| T3.3 | Joint guarantee over the three alarms; tolerances α_k allocated by consequence | M18–M24 |
| T3.4 | Back-testing on the historical record and on storylines beyond it | M22–M27 |
| T3.5 | Alarm refinement with the outcomes of the live operation | M28–M34 |

Deliverables: D3.1 Certified alarm algorithms and proofs (Month 24); D3.2 Back-testing report (Month 27)

WP4. Monitoring network designed for the warnings   (Months 1–36; objective O4)

Objective: Choose the sensors jointly for their value to the three warnings, install them, keep them running and feed them into the model.

| Task | Description | Months |
| --- | --- | --- |
| T4.1 | Goal-oriented design across sensor types: piezometers with conductivity, chloride sampling, GNSS, seismic noise, nodes, fibre | M1–M6 |
| T4.2 | Procurement and installation | M4–M12 |
| T4.3 | Operation, quality control, data streaming and assimilation | M12–M36 |
| T4.4 | Seismic velocity calibrated against the water table at the port or landfall | M12–M24 |

Deliverables: D4.1 Network design report (Month 6); D4.2 Network installed and streaming (Month 12)

WP5. Live demonstration at the wellfields, port and landfall   (Months 22–36; objective O5)

Objective: Run the system live for twelve months with the operators and civil protection, evaluate every operating decision against all three hazards, and execute the post-event protocol whenever it is triggered.

| Task | Description | Months |
| --- | --- | --- |
| T5.1 | Bulletin protocol and decision interfaces with the operators and civil protection | M22–M23 |
| T5.2 | Twelve months of live operation, bulletins logged and outcomes verified | M23–M34 |
| T5.3 | Pumping rule evaluated against the three hazards together and agreed with the water utility | M24–M33 |
| T5.4 | Post-event protocol after strong earthquakes or surges (on trigger) | M12–M36 |

Deliverables: D5.1 Live demonstration report (Month 34)

WP6. Training, transfer and dissemination   (Months 1–36; objective O6)

Objective: Build lasting capacity: early-career researchers trained by doing, operator staff trained to run the system unaided, open software and data, and procedures the operators and authorities can adopt.

| Task | Description | Months |
| --- | --- | --- |
| T6.1 | Early-career researchers: exchanges, schools and supervised work in WP1–WP5 | M3–M36 |
| T6.2 | Training of operator and civil-protection staff | M24–M36 |
| T6.3 | Open software and data release with documentation | M30–M33 |
| T6.4 | Operating procedures and policy brief | M30–M36 |

Deliverables: D6.1 Software and data release (Month 33); D6.2 Operating procedures and policy brief (Month 36)

WP7. Management, data and risk   (Months 1–36; objective all)

Objective: Coordinate the consortium, secure data access from the operators, manage risks and report.

| Task | Description | Months |
| --- | --- | --- |
| T7.1 | Coordination, steering committee, reporting | M1–M36 |
| T7.2 | Data management and access agreements with the water utility, port and landfall operators | M1–M3 |
| T7.3 | Risk and quality management | M1–M36 |

Deliverables: D7.1 Data management plan and access agreements (Month 3); D7.2 Progress reports (Month 12); D7.2 Progress reports (Month 24); D7.3 Final report (Month 36)

3. Milestones

|  | Month | Milestone | Means of verification |
| --- | --- | --- | --- |
| MS1 | 6 | Network design agreed | D4.1 approved by the steering committee and the operators |
| MS2 | 12 | Network streaming; coastal motion known | D4.2 (≥ 90% data availability over the first month) and D1.1 delivered |
| MS3 | 18 | Coupled model calibrated | D2.1: held-out observations reproduced within their stated uncertainty |
| MS4 | 22 | Go/no-go for live operation | D2.2 surrogate error bound met on the test set; alarm prototype passes a dry run |
| MS5 | 27 | Miss-rate targets confirmed in back-testing | D3.2: each miss rate ≤ α_k with its confidence interval reported |
| MS6 | 34 | Twelve months of live operation completed | D5.1 with the bulletin log and verified outcomes |
| MS7 | 36 | Hand-over to the operators | D6.2 procedures adopted; operator staff run the system unaided |

4. Risks and mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Operators delay access to well, port or landfall data | Medium | High | Access agreements signed by Month 3 (D7.1); public and remote-sensing data allow WP1 and the design in WP4 to start regardless |
| InSAR loses coherence on vegetated plains or on new port works | Medium | Medium | Corner reflectors and GNSS at the assets (T1.2); persistent-scatterer processing on built structures |
| Fibre-optic access not granted | Medium | Low | Seismic noise from stations and temporary nodes gives the same velocity signal at lower resolution |
| No strong earthquake or surge during the demonstration | High | Medium | Guarantees are tested in back-testing over the historical record, including the 2019 earthquake, and on storylines beyond it (T3.4) |
| Surrogate fails its error bound in part of the domain | Low | Medium | Bound triggers fall-back to the full model on a reduced domain for those forecasts; the alarm margin widens automatically |
| Equipment procurement or customs delays | Medium | Medium | Orders placed in Month 4; installation window to Month 12 with priority given to the sensors ranked highest in D4.1 |
| Loss of trained staff at the operators | Medium | Medium | Several staff trained per operator; procedures and software documented for use without the project team |