CERTAIN-COAST — Deliverables

Certified early warning for seawater intrusion, liquefaction and extreme sea levels at the wellfields, port and energy landfall of a subsiding Adriatic coast

CERTAIN-COAST produces 14 deliverables over 36 months: 2 public, 4 restricted to the operators, authorities or the SPS Programme, and 8 with a public part and a restricted annex, following the two-tier dissemination plan. Each deliverable has an acceptance test stated in advance; three of them decide the evidence gates at Months 18, 22 and 27. Months count from the start of the grant.

1. Deliverables at a glance

| No. | Deliverable | WP | Lead | Type | Access | Month | Milestone |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D7.1 | Data management plan and access agreements | WP7 | [NPD team] (coordinator) | Report | Public + restricted annex | M3 | — |
| D4.1 | Network design report | WP4 | [NPD team] | Report | Restricted | M6 | MS1 |
| D1.1 | Coastal motion atlas and R(t) series | WP1 | [NPD team] or [additional NATO co-director] | Data, report | Public + restricted annex | M12 | MS2 |
| D4.2 | Network installed and streaming | WP4 | [NPD team] | Demonstrator | Restricted | M12 | MS2 |
| D7.2 | Progress reports | WP7 | [NPD team] (coordinator) | Report | Restricted | M12 | — |
| D2.1 | Calibrated coupled model | WP2 | [PPD team] | Model | Public + restricted annex | M18 | MS3 (gate) |
| D2.2 | Certified surrogate | WP2 | [PPD team] | Software | Public + restricted annex | M22 | MS4 (gate) |
| D3.1 | Certified alarm algorithms and proofs | WP3 | [PPD team] | Report | Public | M24 | — |
| D7.2 | Progress reports | WP7 | [NPD team] (coordinator) | Report | Restricted | M24 | — |
| D3.2 | Back-testing report | WP3 | [PPD team] | Report | Public + restricted annex | M27 | MS5 (gate) |
| D6.1 | Software and data release | WP6 | [PPD team] | Software, data | Public | M33 | — |
| D5.1 | Live demonstration report | WP5 | [NPD team] | Report | Public + restricted annex | M34 | MS6 |
| D6.2 | Operating procedures and policy brief | WP6 | [PPD team] | Report | Public + restricted annex | M36 | MS7 |
| D7.3 | Final report | WP7 | [NPD team] (coordinator) | Report | Public + restricted annex | M36 | — |

Figure 1. Deliverables by month and work package. Marker shows the access level; dashed lines mark the three evidence gates.

2. Deliverable descriptions

D7.1  Data management plan and access agreements   WP7 · Month 3 · Report · Public + restricted annex

| Contents | Data management plan (version 1); signed access agreements with the operators; data classification for the release gate. |
| --- | --- |
| Acceptance test | Access agreements signed by the operators; data management plan approved by the steering committee. |
| Format and where | Report; data plan public, agreements restricted. |
| Reviewed by | Steering committee |
| Depends on | Commitment letters |
| Feeds | All work packages |

D4.1  Network design report   WP4 · Month 6 · Report · Restricted

| Contents | Ranking of every candidate sensor by its value for the three warnings per unit cost; the chosen network within budget; installation and access plan. |
| --- | --- |
| Acceptance test | Approved by the steering committee and the operators (MS1). |
| Format and where | Report, restricted (sensor locations inside sites). |
| Reviewed by | Steering committee; operators |
| Depends on | Preliminary sensitivities (WP2); access (D7.1) |
| Feeds | D4.2; procurement (T4.2) |

D1.1  Coastal motion atlas and R(t) series   WP1 · Month 12 · Data, report · Public + restricted annex

| Contents | Vertical and east velocity maps of the three asset areas from Sentinel-1 (2014 onward) and GNSS; elastic and inelastic compaction parameters and the head limit h_pc; the 2019 coseismic and postseismic motion; relative sea level R(t) with uncertainty at each asset. |
| --- | --- |
| Acceptance test | Vertical-velocity uncertainty of the order of 1–2 mm/yr at asset points; InSAR and GNSS agree within their uncertainty. |
| Format and where | Report and gridded data (GeoTIFF, NetCDF); regional maps in Zenodo, asset-point values to the operators. |
| Reviewed by | WP2 lead; operators for asset points |
| Depends on | T1.1–T1.3; GNSS and corner reflectors (D4.2) |
| Feeds | WP2 sea boundary; WP3 extremes; WP5 pumping limit |

D4.2  Network installed and streaming   WP4 · Month 12 · Demonstrator · Restricted

| Contents | Installed piezometers and loggers, GNSS, corner reflectors and seismic stations, with telemetry, quality control and data streaming. |
| --- | --- |
| Acceptance test | At least 90% data availability over the first month (MS2). |
| Format and where | Demonstrator and installation report, restricted. |
| Reviewed by | WP7; operators |
| Depends on | D4.1; procurement |
| Feeds | D1.1; D2.1; WP5 |

D7.2  Progress reports   WP7 · Months 12 and 24 · Report · Restricted

| Contents | Progress, deliverables and milestones; risk register; indicators (results, dissemination, gender, ethics); spending against the budget. |
| --- | --- |
| Acceptance test | Submitted to the SPS Programme on time and accepted. |
| Format and where | Report to the SPS Programme, restricted. |
| Reviewed by | Steering committee |
| Depends on | All work packages |
| Feeds | NATO SPS |

D2.1  Calibrated coupled model   WP2 · Month 18 · Model · Public + restricted annex

| Contents | Set-up of the coupled model (variable-density flow, salt memory, compaction, liquefaction factor of safety, coastal water level); calibrated parameters from ES-MDA; validation on held-out data. |
| --- | --- |
| Acceptance test | Held-out heads, chloride, InSAR and seismic velocity fall inside the 90% predictive intervals at close to the nominal rate (gate MS3). |
| Format and where | Model files and report; site version restricted, synthetic-coast version public. |
| Reviewed by | Steering committee; WP3 lead |
| Depends on | D1.1; data from D4.2; operator records (D7.1) |
| Feeds | D2.2; WP3; WP4 refinement |

D2.2  Certified surrogate   WP2 · Month 22 · Software · Public + restricted annex

| Contents | Trained neural or kernel operator of the coupled model; adjoint-weighted error indicator; conformal quantile; test report on held-out full-model runs. |
| --- | --- |
| Acceptance test | Coverage of the error bound at least 1 − δ on test runs; thousands of storylines per day; alarm prototype passes a dry run (gate MS4). |
| Format and where | Software and report; site version restricted, synthetic-coast version public (ONNX). |
| Reviewed by | Steering committee; WP5 lead |
| Depends on | D2.1 |
| Feeds | D3.1; live operation (WP5) |

D3.1  Certified alarm algorithms and proofs   WP3 · Month 24 · Report · Public

| Contents | Construction of the three-part margin; proofs of the miss-rate bound for each alarm and of the joint bound; allocation of tolerances by consequence; implementation with unit tests. |
| --- | --- |
| Acceptance test | Proofs checked by a reviewer outside WP3; implementation passes its tests and reproduces the synthetic examples. |
| Format and where | Report (public) and code (released with D6.1). |
| Reviewed by | Independent reviewer; steering committee |
| Depends on | D2.2; thresholds agreed in T3.1 |
| Feeds | D3.2; WP5 bulletins |

D3.2  Back-testing report   WP3 · Month 27 · Report · Public + restricted annex

| Contents | Back-testing of the full chain over the record since 2014 and on storylines beyond it (drought, compound storm, 2019-type earthquake, increased pumping), under a protocol frozen before the results. |
| --- | --- |
| Acceptance test | Miss rate of each alarm at or below its target with Clopper–Pearson intervals; false-alarm rate reported (gate MS5). |
| Format and where | Report; protocol published with a DOI before the results; aggregated results public, asset annex restricted. |
| Reviewed by | Steering committee; operators |
| Depends on | D3.1; D2.2; D1.1 |
| Feeds | WP5; D5.1; papers |

D6.1  Software and data release   WP6 · Month 33 · Software, data · Public

| Contents | Open software (model, surrogate, alarms, network design) with documentation, tests and containers; the synthetic test coast; open datasets; verification statistics. |
| --- | --- |
| Acceptance test | Release with a DOI; installed and run on the synthetic coast by someone outside the project team. |
| Format and where | Software (Apache-2.0) and data (CC BY 4.0) in Zenodo and a public repository. |
| Reviewed by | External tester; WP2 and WP3 leads |
| Depends on | D2.2; D3.1; D1.1 |
| Feeds | Transfer workshop; other coasts |

D5.1  Live demonstration report   WP5 · Month 34 · Report · Public + restricted annex

| Contents | Twelve months of bulletins to the operators and civil protection; the bulletin log with outcomes; verification of the miss and false-alarm rates; the joint pumping rule; post-event protocol executions. |
| --- | --- |
| Acceptance test | Observed miss rates within targets with confidence intervals; bulletin log complete and reproducible (MS6). |
| Format and where | Report; verification statistics public, asset annex restricted. |
| Reviewed by | Steering committee; operators; civil protection |
| Depends on | D3.1–D3.2; D4.2; D2.2 |
| Feeds | D6.2; D7.3; papers |

D6.2  Operating procedures and policy brief   WP6 · Month 36 · Report · Public + restricted annex

| Contents | Operating procedures for the wellfields, the port and the landfall, and the post-event protocol; a policy brief for the national authorities. |
| --- | --- |
| Acceptance test | At least one procedure adopted per asset; policy brief delivered to the national authorities (MS7). |
| Format and where | Procedures restricted to the operators; public version of the policy brief. |
| Reviewed by | Operators; civil protection |
| Depends on | D5.1 |
| Feeds | Hand-over; national policy |

D7.3  Final report   WP7 · Month 36 · Report · Public + restricted annex

| Contents | Results, verification of the guarantees, hand-over and sustainability arrangements, spending, and lessons for other coasts. |
| --- | --- |
| Acceptance test | Submitted to the SPS Programme and accepted; public summary released. |
| Format and where | Report; public summary, full report restricted. |
| Reviewed by | Steering committee |
| Depends on | All deliverables |
| Feeds | NATO SPS; follow-up funding |

3. Quality assurance

• Owner. Each deliverable has a responsible author in the leading work package and a reviewer from another work package or outside the project.

• Timing. A complete draft is circulated four weeks before the due month and reviewed within two weeks.

• Release gate. Every deliverable is classified (public, restricted or both) and, if it uses operator data, sent to the operators for review of sensitive content before release.

• Acceptance. The steering committee checks the acceptance test of each deliverable; for D2.1, D2.2 and D3.2 the result decides the evidence gate (MS3, MS4, MS5).

• Version control. Deliverables, data and code are versioned; each public deliverable gets a persistent identifier.

4. What is new in these deliverables

• Every deliverable has a pass test. Each states in advance how it will be judged, and three of them decide whether the project moves on (gates at Months 18, 22 and 27).

• The central claim is registered before it is tested. The back-testing protocol of D3.2 is published with a DOI before the results are computed.

• Open and restricted in one deliverable. Mixed deliverables have a public part (methods, verification) and a restricted annex (asset-level results), so openness never exposes critical infrastructure.

• A stranger can run it. D6.1 is accepted only when someone outside the team installs the software and reproduces the synthetic coast.

• Guarantees checked in public. D5.1 publishes the observed miss and false-alarm rates of the live warnings, so anyone can check the certified rates.